## Formal
BID PROJECT PLAN (Formal)
Bid Number: |  |  | Project Director:
Project Number: |  |  | Project Manager:
Project Name: |  |  | Senior Buyer:
Campus: |  |  | Architect/Engineer Firm:
Bond Measure: |  |  | DSA Required:
Requisition Number: |  |  | DSA Approval Date:
FOAP:
Scope of Work:
Description for PlanetBids
$ Project Estimate: |  | Project Stabilization Agreement:
Planned Duration: |  | Job Walk:
Total Allowance: |  | Prime Contractor License(s) Required:
Alternates:
Documents Included: | Describe type of document e.g. As-Builts, Hazmat, Geotech, Drawings
BID CALENDAR
ACTIVITY |  |  |  |  | DATES
Final edits completed by Project Manager on bid specs & drawings: |  |  |  | = | #VALUE! | -71
Approved plans, specifications/drawings, and provides PR# to Purchasing: |  |  |  | = | #VALUE! | -64
Purchasing edits bid document: |  |  |  | = | #VALUE! | -62
Purchasing finalizes document for PlanetBids posting: |  |  |  | = | #VALUE! | -58
Purchasing submits Advertisement for Publication (if required): |  |  |  | = | #VALUE! | -57
ADVERTISEMENT POSTED, BID RELEASE ON PLANETBIDS: |  |  |  | = | #VALUE! | -54
Job Walk Date and Time: |  |  |  | = | #VALUE! | -45
Deadline for Questions: |  |  |  | = | #VALUE! | -38
Final Addendum (72 hours min. before due date): |  |  |  | = | #VALUE! | -24
BIDS DUE: |  |  |  | = | #VALUE! | -21
Bid Review: |  |  |  | = | #VALUE! | -20
Issue Notice of Intent to Award: |  |  |  | = | #VALUE! | -16
Board submittal deadline: |  |  |  | = | #VALUE! | -11
BOARD MEETING DATE: |  |  |  | = | Sat
Issue Notice of Award: |  |  |  | = | Sun | 1899-12-31
Contract Executed: |  |  |  | = | Sat
Notice to Proceed: |  |  |  | = | Sat
Enter Board meeting date first. Recommended dates will auto populate, adjust for weekends and project timeline requirements.
Revision Date:
Additional notes for Purchasing, add as needed:
Ver. Jan 2024

## Informal
BID PROJECT PLAN (Informal)
Bid Number: |  |  | Project Director:
Project Number: |  |  | Project Manager:
Project Name: |  |  | Senior Buyer:
Campus: |  |  | Architect/Engineer Firm:
Bond Measure: |  |  | DSA Required:
Requisition Number: |  |  | DSA Approval Date:
FOAP:
Scope of Work:
Description for PlanetBids
$ Project Estimate: |  | Project Stabilization Agreement:
Planned Duration: |  | Job Walk:
Total Allowance: |  | Prime Contractor License(s) Required:
Alternates:
Documents Included: | Describe type of document e.g. As-Builts, Hazmat, Geotech, Drawings
BID CALENDAR
ACTIVITY |  |  |  |  | DATES
Final edits completed by Project Manager on bid specs & drawings: |  |  |  | = | #VALUE! | -43
Approved plans, specifications/drawings, and provides PR# to Purchasing: |  |  |  | = | #VALUE! | -38
Purchasing edits bid document: |  |  |  | = | #VALUE! | -36
Purchasing finalizes document for PlanetBids posting: |  |  |  | = | #VALUE! | -32
BID RELEASE ON PLANETBIDS: |  |  |  | = | #VALUE! | -31
Job Walk Date and Time: |  |  |  | = | #VALUE! | -25
Deadline for Questions: |  |  |  | = | #VALUE! | -20
Final Addendum (72 hours min. before due date): |  |  |  | = | #VALUE! | -13
BIDS DUE: |  |  |  | = | #VALUE! | -10
Bid Review: |  |  |  | = | #VALUE! | -9
Issue Notice of Intent to Award: |  |  |  | = | #VALUE! | -5
Issue Notice of Award: |  |  |  | = | Sat
Contract Executed: |  |  |  | = | Sat
Notice to Proceed: |  |  |  | = | Sat
Enter Notice of Award date first. Recommended dates will auto populate, adjust for weekends and project timeline requirements.
Revision Date:
Additional notes for Purchasing, add as needed:
Ver. Jan 2024