## Sheet1
RFP PROJECT PLAN
RFP Number: |  |  | Project Director:
Project Number: |  |  | Project Manager:
Project Name: |  |  | Senior Buyer:
Campus: |  |  | RFP Type:
Bond Measure:
Requisition Number:
FOAP:
Scope of Work:
Description for PlanetBids
Selection Committee
Evaluator Name: |  | Evaluator Name:
Evaluator Name: |  | Evaluator Name:
Evaluator Name: |  | Evaluator Name:
Services Needed: | Architect, Engineer, Inspector of Record, etc.
RFP CALENDAR
ACTIVITY |  |  | DATES
Draft RFP to Purchasing: |  | = | #VALUE! | -73
Selection Committee Meeting - RFP Review: |  | = | #VALUE! | -70
Finalize RFP with Purchasing: |  | = | #VALUE! | -67
Purchasing finalizes document for PlanetBids posting: |  | = | #VALUE! | -65
Purchasing submits Advertisement for Publication (if required): |  | = | #VALUE! | -64
ADVERTISEMENT POSTED, RFP RELEASE ON PLANETBIDS: |  | = | #VALUE! | -61
Second Advertisement: |  | = | #VALUE! | -54
Pre-Proposal Conference (if applicable): |  | = | #VALUE! | -47
Deadline for Questions: |  | = | #VALUE! | -40
Final Addendum (72 hours min. before due date): |  | = | #VALUE! | -31
PROPOSALS DUE: |  | = | #VALUE! | -28
Selection Committee Meeting - Proposal Scoring |  | = | #VALUE! | -21
Selection Committee Meeting - INTERVIEWS (if applicable) |  | = | #VALUE! | -16
Notice of Intent to Award: |  | = | #VALUE! | -15
Board submittal deadline: |  | = | #VALUE! | -11
BOARD MEETING DATE: |  | = | Sat
Issue Notice of Award: |  | = | Sun | 1899-12-31
Contract Executed: |  | = | Sat
Enter Board meeting date first. Recommended dates will auto populate, adjust for weekends and project timeline requirements.
Revision Date:
Additional notes for Purchasing, add as needed:
Ver. Jan 2024